## Instructions
Knowledge Audit Workbook — Instructions
This workbook combines the implementation schedule and content inventory into one package.
SHEETS
Implementation Schedule — 30 tasks across 6 phases with a 14-week Gantt timeline.
Content Inventory — Catalog every document across all platforms. One row per document.
Summary — Formula-driven rollup of inventory status, priorities, and actions.
HOW TO USE
1. Start with the Implementation Schedule. Use it to plan and track progress through each phase.
2. During Phase 2 (Inventory), switch to the Content Inventory tab and add one row per document.
3. Use dropdown menus in Platform, Content Type, Status, Duplicates, Priority, and Action columns.
4. For the initial pass, focus on Title, Platform, Location, Content Type, and Status.
5. Distribute sections to engineering leads for status review (Current / Outdated / Unknown).
6. During Phase 3 (Triage), fill in Owner, Priority, and Action columns.
7. Check the Summary tab for rollup counts at any point.
INVENTORY COLUMN DEFINITIONS
ID — Sequential identifier (001, 002, etc.).
Document Title — Name as it appears in the source platform.
Platform — Where it lives (Google Drive, SharePoint, local drive, etc.).
Folder / Path — Location within the platform.
URL or Link — Direct link if available.
Content Type — Category: runbook, integration guide, onboarding, gap (not yet documented), etc.
Last Modified — Date last changed.
Last Modified By — Person who last edited. 'Unknown' if not determinable.
Status — Current, Outdated, Unknown, Needs Review, or Superseded.
Duplicates? — Whether duplicate or near-duplicate versions exist elsewhere.
Owner (Assigned) — Person responsible for this document going forward.
Priority — High / Medium / Low based on impact and usage.
Action — Triage decision: Keep & Update, Rewrite, Archive, Delete, Merge, or Reassign. (Needs Review is a Status, not an Action.)
Notes — Additional context, links to duplicates, or audit observations.
TIPS
- Don't read every document in the first pass. Build the map first, edit later.
- Give engineering leads a two-week deadline to review their sections.
- Four sample rows are on the Content Inventory sheet. Delete them when ready.
- The schedule task durations assume a 20–150 person company. Scale up for larger orgs.
- Use "Gap — Not Yet Documented" as the Content Type for processes or docs that should exist but don't.
- The Summary tab tracks gap count separately so you can report them to leadership.
- Biweekly status updates to leadership are built into the schedule (Phase 1, Wk 3–14).
- Adapt the workbook to your company. Add columns, rename categories, outgrow it.

## Implementation Schedule
Phase | Task | Owner | Effort Level | Duration | Deliverable | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1. Get the Mandate | Draft one-page problem statement | Tech Writer | Low | 3–4 days | Problem statement doc
| Collect 2–3 concrete examples of outdated/conflicting docs | Tech Writer | Low | 1–2 days | Examples list | bar: Wk 1
| Identify engineering contact for audit support | Tech Writer | Low | 1 day | Named contact | bar: Wk 1
| Present problem statement to leadership; get sign-off | Tech Writer | Low | 1 meeting | Approved mandate | bar: Wk 1 to Wk 2
| Deliver status update to leadership (biweekly, Wk 3–14) | Tech Writer | Low | 30 min each | Status update (Summary tab metrics) | bar: Wk 3 to Wk 14
2. Inventory | List all platforms where content lives | Tech Writer | Low | 1 day | Platform list
| Create inventory spreadsheet (use Content Inventory tab) | Tech Writer | Low | 1 day | Inventory workbook | bar: Wk 3
| Populate inventory: Google Drive | Tech Writer | Moderate | 3–5 days | Drive inventory rows | bar: Wk 3 to Wk 4
| Populate inventory: SharePoint | Tech Writer | Moderate | 3–5 days | SharePoint inventory rows | bar: Wk 4 to Wk 5
| Populate inventory: local/shared drives | Tech Writer + Eng | Moderate | 2–3 days | Local drive inventory rows | bar: Wk 5 to Wk 6
| Distribute sections to engineering leads for status review | Tech Writer | Low | 1 day | Assigned review sections | bar: Wk 5
| Engineering leads flag status (Current / Outdated / Unknown) | Eng Leads | Moderate | 2 weeks | Completed status column | bar: Wk 5 to Wk 6
3. Triage | Sort inventory into four buckets (Keep / Rewrite / Archive / Delete) | Tech Writer | Moderate | 3–4 days | Triaged inventory
| Run triage meeting with engineering leads (high-priority items) | Tech Writer + Eng Leads | Moderate | 1–2 meetings | Triage decisions documented | bar: Wk 7 to Wk 8
| Assign document owners where missing | Tech Writer + Eng Leads | Low | During triage mtg | Owner column filled | bar: Wk 7 to Wk 8
4. Consolidate Platforms | Decide on single primary platform | Tech Writer + IT | Low | 1 meeting | Platform decision
| Define folder/space structure and naming conventions | Tech Writer | Moderate | 2–3 days | Structure doc | bar: Wk 9
| Migrate 'Keep & Update' content to primary platform | Tech Writer + Eng | High | 5–8 days | Migrated content | bar: Wk 9 to Wk 11
| Set up archive location; move archived content | Tech Writer | Moderate | 2–3 days | Archive folder populated | bar: Wk 11 to Wk 12
| Delete content marked for deletion | Tech Writer | Low | 1 day | Cleanup complete | bar: Wk 12
5. Establish Governance | Define ownership, review cycle, deprecation process | Tech Writer | Low | 2–3 days | Governance rules doc
| Write new-content checklist | Tech Writer | Low | 1 day | Checklist | bar: Wk 13
| Post governance rules in primary platform | Tech Writer | Low | 1 day | Published rules | bar: Wk 13
| Walk engineering teams through governance process | Tech Writer | Low | 1–2 meetings | Teams briefed | bar: Wk 13 to Wk 14
6. Engineering Integration | Add 'docs impact' checkbox to PR templates | Tech Writer + Eng Lead | Low | 1 hour | Updated PR template
| Add docs check to sprint retro agenda | Tech Writer | Low | 1 hour | Updated retro template | bar: Wk 13
| Set up new-hire doc feedback process | Tech Writer + HR | Low | 1 day | Onboarding doc feedback form | bar: Wk 14
| Assign first rotating 'docs buddy' per team | Eng Leads | Low | 1 meeting | Buddies assigned | bar: Wk 14
| Weekly maintenance (ongoing after launch) | Tech Writer | Low | 2–4 hrs/week | Ongoing | bar: Wk 14
Total Duration | 7–14 weeks for initial cleanup. 2–4 hrs/week ongoing maintenance after.
Gantt Legend
Phase 1: Get the Mandate
Phase 2: Inventory
Phase 3: Triage
Phase 4: Consolidate Platforms
Phase 5: Establish Governance
Phase 6: Engineering Integration

## Content Inventory
ID | Document Title | Platform | Folder / Path | URL or Link | Content Type | Last Modified | Last Modified By | Status | Duplicates? | Owner (Assigned) | Priority | Action | Notes
001 | NetSuite Connector Setup | Google Drive | /Engineering/Integrations/ |  | Integration Guide | 2024-03-15 | J. Smith | Outdated | Yes - See Notes |  | High | Rewrite | Superseded by v2.1 doc in SharePoint. Engineers still referencing this version.
002 | New Hire Onboarding Checklist | SharePoint | /HR/Onboarding/ |  | Onboarding | 2025-11-01 | M. Johnson | Current | None Found | M. Johnson | Medium | Keep & Update
003 | API Error Codes Reference | Local Drive | C:\Users\dev\docs\ |  | API Reference | 2024-06-22 | Unknown | Unknown | Suspected |  | High | Reassign | Found on former employee's shared folder backup. May duplicate Intercom article.
004 | [GAP] Integration rollback procedure | N/A — Not Yet Documented |  |  | Gap — Not Yet Documented |  |  | Needs Review | Not Checked |  | High | Rewrite | Discovered during audit. No written rollback procedure exists. Engineering lead confirmed it is verbal only.

## Summary
Knowledge Audit Summary
Total Documents | 4
Status: Current | 1
Status: Outdated | 1
Status: Unknown | 1
Status: Needs Review | 1
Status: Superseded | 0
Duplicates Identified | 1
Duplicates Suspected | 1
Priority: High | 3
Priority: Medium | 1
Priority: Low | 0
Action: Keep & Update | 1
Action: Rewrite | 2
Action: Archive | 0
Action: Delete | 0
Action: Merge | 0
Action: Reassign | 1
Gaps Identified (Not Yet Documented) | 1
No Owner Assigned | 3